## Milestone Tickets
ID | Phase | Title | Track | Blocked By | Unlocks | Description | Acceptance Criteria | Refs | Status
IO-W0-01 | W0 | BiomeRegionData ScriptableObject pipeline | Engineering + Design | Exposure zone kinds (shipped) | IO-W1-01, IO-W2-01 | Create `BiomeRegionData` SO with pressure profile, exploration verb tags, weather weight table, vehicle allow tags (B1–B7). Editor create menu + validation for campaign unlock order field. | - [ ] SO holds: biome ID, display name, dominant pressures, verb list, weather weights, vehicle tags, unlock phase enum - [ ] Seven assets stubbed (B1–B7) matching biome plan table - [ ] Journal can read biome ID for fog/tab display (stub OK) - [ ] No hardcoded Invector names in new types | Biome plan E0, §3; Phase map W0. | Open
IO-W0-02 | W0 | Ecology organism registry (IDs + metadata) | Engineering + Design | — | IO-W2-03, IO-W3-04 | Registry mapping organism ID → tier, category (flora/fauna/android/humanoid/machine), biome bias, `SurfaceThreatKind` where applicable. Data-only; prefabs optional. | - [ ] All roster anchor names from `Io_Biome_Ecology_Roster.md` §1.1, §4, §5–6 have stable string IDs - [ ] Void Stitcher registered as global elite - [ ] Rust Garden flagged machine-coral (not fauna) - [ ] Editor CSV or SO import path documented in ticket comment | Ecology roster full doc. | Open
IO-W0-03 | W0 | PetDefinition schema (core 12 + vanity + DLC flag) | Engineering | — | IO-W2-05, IO-W3-06 | `PetDefinition` SO: `isVanityExtra`, `isDlc`, acquisition enum (Stray, Tame, Capture, SalvageRepair, Quest), skill tags (MinorDps, Cc, Loot, Utility, Vanity), biome unlock mask. | - [ ] 12 core + 4 vanity rows authored as data (placeholder icons OK) - [ ] Acquisition enum matches ecology §4.6.2 grammar - [ ] DLC flag present; no runtime shop coupling | Ecology roster §4.6. | Open
IO-W0-04 | W0 | Encounter table templates per biome category | Engineering | IO-W0-02 | IO-W2-04, IO-W7-02 | `SurfaceEncounterTable` template assets for Alien / Lifeform / Android per biome family; document combat zone humanoid cap default. | - [ ] At least one template per threat category - [ ] `SurfaceEncounterZone` can pick by anchor `PreferredThreatKind` - [ ] Weight fields documented for ExperienceDirector handoff (IO-W7-01) | GDD A2 surface encounters; Phase map W0. | Open
IO-W0-05 | W0 | ExperienceDirector stubs (biome weights + elite pool) | Systems | GDD B4 #1 World Engine spine | IO-W7-01 | Read-only stubs: biome weight snapshot, elite pool entry for Void Stitcher (max 1/expedition), Echo cap placeholders. | - [ ] Director compiles; no runtime spawn until IO-W7-01 - [ ] Void Stitcher slot documented with seam-volume trigger enum stub - [ ] Unit test or debug menu prints weight table from B6→B7 order | Biome plan §2.8; Ecology §3.5. | Open
IO-W1-01 | W1 | Full-scale main map blockout (colony + B6 hub + mountains) | World art + Engineering | IO-W0-01, terrain/streaming plan | IO-W2-01, IO-W2-02 | Greybox full main map: Command Center anchor, B6 Basalt Highlands region, 200–300 m mountain zones, road/path tags for future vehicles. | - [ ] Player spawns at colony; can foot-travel into B6 hub zone - [ ] Region boundaries align with `BiomeRegionData` B6 asset - [ ] Exposure volumes placed for B6 mixed pressures (stub values OK) - [ ] Map fog: colony + B6 sector reveal test hook | Biome plan E1; Phase map W1. | Open
IO-W1-02 | W1 | Underground instance pipeline (breach teleport + anchor) | Engineering | IO-W1-01 | IO-W2-06, IO-W5-01 | Breach interact → load underground scene → exit returns to surface anchor position. Vehicle auto-pack volume 10–20 m at entry; manual unpack on exit. | - [ ] Enter/exit prompt works; trio follows through teleport - [ ] Surface anchor stored per breach ID - [ ] Hovercraft auto-packs in entry zone; foot-only inside instance - [ ] One test Stratum 1 greybox scene wired | Biome plan E1b, §2.5; Underground P0. | Open
IO-W1-03 | W1 | Walk-in shallow tubes (no teleport) | World art | IO-W1-01 | IO-W2-06 | Colony refuge tubes + one B6 skylight mouth as on-map geometry (additive scene OK); no loading screen. | - [ ] Foot transition colony ↔ refuge tube without teleport - [ ] O₂ relief volume in refuge (design targets from underground plan) - [ ] Documented list of walk-in exceptions matches biome plan §2.5 | Biome plan §2.5; Underground plan §0. | Open
IO-W1-04 | W1 | Stratum 1 greybox module kit | World art | IO-W1-02 | IO-W5-01 | Minimal tube modules: straight, curve, T, skylight, collapse — modular greybox only. | - [ ] At least 5 module prefabs snap together - [ ] Cave offset volume component reduces surface weather (blocked flag) - [ ] One 3–5 module test loop in instance scene | Underground plan §4.1. | Open
IO-W2-01 | W2 | Biome regions B6, B1, B2 on main map | World art + Design | IO-W1-01, GDD B4 #4 WeatherDirector (sulfur + geyser) | IO-W2-02, IO-W2-03, IO-W2-04 | Author B6 hub, B1 Sulfur Plains, B2 Geyser Fields regions with pressure volumes, POI placeholders, breach anchors to S1/S2. | - [ ] All three regions pass ecology checklist §5 (blockout level) - [ ] B6 multi-breach choice: at least 2 breach POIs with different pressure labels - [ ] B1 storm lane shelter rocks placed; B2 vent nodes with telegraph audio hooks - [ ] Campaign unlock: B6→B1→B2 gating via WorldState or quest stub | Phase map W2; Biome plan §4 B1/B2/B6. | Open
IO-W2-02 | W2 | Activity templates v1 (Recon, Harvest, Nest Clear) | Systems + Design | IO-W2-01 | IO-W7-03 | Three activity templates drivable by director or manual quest: Recon Scan, Harvest Window, Nest Clear — wired to B1/B2/B6 POIs. | - [ ] Each template completable once in test scene - [ ] Nest Clear tied to Vent Crab queen POI (B2) or jackal pack (B6) - [ ] Harvest Window respects sulfur storm abort (WeatherDirector hook) | Biome plan §6. | Open
IO-W2-03 | W2 | Ecology content batch 1 (flora + fauna POIs) | Content | IO-W0-02, IO-W2-01 | IO-W3-03 | Place harvest/hazard flora and fauna for B1, B2, B6 per phase map table. Placeholder meshes acceptable; behaviors from encounter registry. | - [ ] B1: Brimstone Fan, Haze Spore Shelf, Cinder Skitter, Sulfur Hound pack - [ ] B2: Geyser Pod, Vent Crab nest, Plume Moth ambient - [ ] B6: Tube Lace Shelf, Tube Jackal pack, Cave Scout Moth ambient - [ ] Graveyard: Scrapper Drone + Survey Drone on one wreck each | Ecology roster B1/B2/B6 sections. | Open
IO-W2-04 | W2 | Surface encounters B1/B2/B6 | Engineering + Content | IO-W0-04, IO-W2-03 | IO-W7-02 | `SurfaceEncounterZone` + tables for first regions; patrol routes on jackals/hounds. | - [ ] Zones spawn on region enter; humanoid cap respected - [ ] Alien/Lifeform/Android categories represented per GDD A2 - [ ] Patrol loop + ping-pong on at least one route | GDD A2; Phase map W2 threats. | Open
IO-W2-05 | W2 | Pet system foundation (Pet Bay + inventory + retire placeholders) | Engineering | IO-W0-03, GDD B4 #6 pet fold | IO-W2-07, IO-W3-06 | Pet Bay terminal; owned-pet inventory; one active pet on expedition; remove/disable Ricky, Probe, Fox Cub from ship paths; UI tab fold toward Companions/Echoes. | - [ ] Equip/swap pet at colony - [ ] Active pet follows player; does not join trio combat AI - [ ] Legacy pet prefabs not referenced in new game flow - [ ] Save/load persists owned pets list | Ecology §4.6; GDD B4 #6. | Open
IO-W2-06 | W2 | Tame + capture grammar (organic pets) | Systems | IO-W2-05 | IO-W2-07, IO-W4-04 | Trust meter tame flow; capture + colony stabilizer flow for skittish species. | - [ ] Tame: bait/interact over 2-step test (Condensate Snail path) - [ ] Capture: trap item → stabilizer prop → pet inventory unlock - [ ] Failed capture does not kill organism (design tone) | Ecology §4.6.2. | Open
IO-W2-07 | W2 | Pets batch 1 — V1 Puff + C1, C2, C4 | Content + Systems | IO-W2-05, IO-W2-06 | — | Ship first pets: post-prologue **Brimstone Puff** camp stray; **Cinder Skitter Kit**, **Condensate Snail**, **Geyser Strider Fledgling** in B1/B2. | - [ ] Prologue beat: puff wanders to scrap pile; food offer unlocks V1 - [ ] C1 capture in B1; C2 tame at seep; C4 tame at B2 vent field - [ ] Each pet: follow + at least one skill (loot ping, sniff, or vent chirp) - [ ] Vanity puff has no meaningful DPS | Ecology §4.6.3–4.6.4; Phase map pet table. | Open
IO-W3-01 | W3 | Biome regions B3, B4 on main map | World art + Design | IO-W2-01, thermal/volcano HUD | IO-W3-02, IO-W3-03 | B3 Ash Flats, B4 Lava Calderas — foot only B4, heat-tier gate messaging, collapse sink to S3 edge instance. | - [ ] B3 ash gale low-vis zones; ridge recon POI - [ ] B4 rim heat shadows; lava kill volume; no vehicles in B4 - [ ] Ecology checklist §5 blockout for B3/B4 | Biome plan B3/B4. | Open
IO-W3-02 | W3 | Void Stitcher elite implementation | Content + Systems | IO-W0-05, IO-W3-01 | IO-W7-01 | Global seam ambush predator: hide shader, 0.5 s glass-stress telegraph, lunge, disengage. ExperienceDirector max 1/expedition. | - [ ] Spawns from seam/shimmer volumes any biome B1–B7 (not B7 silent puzzles) - [ ] Audio telegraph before damage; Scout sense widens window (if kit live) - [ ] Ops/Aether-9 comms line on first encounter stub - [ ] Does not replace Caldera Mantis apex role in B4 | Ecology §3.5. | Open
IO-W3-03 | W3 | Ecology batch 2 + threat families (B3/B4) | Content | IO-W3-01 | IO-W7-02 | B3/B4 flora/fauna; humanoid scrappers; scrap mite + turret crawler; Ash Glass Wasp embed. | - [ ] B3: Ash Filament Mat, Basalt Jackal, Ash Stalker, dust spout embed - [ ] B4: Caldera Mantis elite POI, Magma Skitter, Heat Kite flyer - [ ] Humanoid: Stim-Sick Scrapper on graveyard POI - [ ] Machines: M1 mite swarm, M2 turret crawler on wreck | Ecology roster §4, B3/B4. | Open
IO-W3-04 | W3 | Machine pet repair loop | Systems | IO-W2-05 | IO-W3-05 | Salvage broken chassis in world → repair queue at Pet Bay → programming choice (Aggressive / Balanced / Loot). | - [ ] Damaged core item in inventory → repair consumes scrap + AC - [ ] Programming choice alters minor skill bias - [ ] Repaired pet enters owned inventory | Ecology §4.6.2 machine path. | Open
IO-W3-05 | W3 | Pets batch 2 — C3, C5, C8, C9, C10 | Content | IO-W3-04, IO-W2-06 | — | Vent Hatchling, Ash Glass Wasp Drone, Brine Rim Snapper, Field Puck, Scrap Mite Handler. | - [ ] C9/C10 require repair loop; organic pets use tame/capture - [ ] Each has minor DPS or loot skill per roster - [ ] Auto-loot radius tuned lower than C7 (future) | Phase map §4 pet table. | Open
IO-W4-01 | W4 | Biome region B5 + polar night thermal | World art + Systems | IO-W3-01, Purification Hub / inoculation loop | IO-W4-02 | B5 Polar Flats; day/night cycle shifts cold pole; foot only; cover-to-cover POIs. | - [ ] Night intensifies cold stress per biome plan §2.6 - [ ] Void Kelp grove scan POI - [ ] Ecology checklist §5 for B5 | Biome plan B5, §2.6. | Open
IO-W4-02 | W4 | Ecology B5 + Magnet Wyrm elite | Content | IO-W4-01 | — | B5 flora/fauna; Magnet Wyrm; Rift Stalker; Cold Spire Hound packs. | - [ ] Magnet Wyrm 0–1 per zone director gate - [ ] Rad pulse + cover sprint gameplay viable - [ ] Smuggler Remnant Android on cache story POI | Ecology roster B5. | Open
IO-W4-03 | W4 | Side quest “Lost Survey” (Beacon Hopper) | Narrative + Systems | IO-W3-04 | IO-W4-04 | B6 quest awarding damaged Beacon Hopper core → repair → C11 pet. | - [ ] Quest completable; rewards repairable chassis - [ ] C11 breach map ping works after repair - [ ] Communications Officer dialogue stub | Ecology C11 card. | Open
IO-W4-04 | W4 | Pets batch 3 + vanity V2, V3 — C6, C7, C11 | Content | IO-W4-02, IO-W4-03, IO-W2-06 | — | Polar Skimmer Pup, Tube Lace Grub (best loot), Plume Mothling, Ridge Pebble Roller. | - [ ] C7 auto-loot radius ≥ all other core pets - [ ] C6 capture night bias documented in POI - [ ] V2/V3 cosmetic skills only; counted as vanity extras not core 12 | Phase map W4. | Open
IO-W5-01 | W5 | Stratum 1–3 instance content | World art + Content | IO-W1-02, IO-W1-04, IO-W2–W4 surface regions | IO-W6-02 | Build S1–S3 instance scenes; surface pairing B1→S1, B2→S2, B4→S3, B5→S2–3, B6 hub. | - [ ] Wade-only pools: slow, stamina drain, no swim - [ ] S3 Basin Mantis ambush POI; Brine Hound pack at rim - [ ] Brood chamber optional dungeon with warden patrol - [ ] Instance camp prop: rest + stash (one far site) | Underground P1–P4; Phase map W5. | Open
IO-W5-02 | W5 | Tremor / flood coupling underground | Systems | WeatherDirector tremor (B4 #4), IO-W5-01 | IO-W7-04 | Tremor Swarm doubles brood spawn; geyser back-pressure floods S2–S3 tubes. | - [ ] Tremor event triggers rockfall + brood wake in S2–S3 - [ ] Flood timer opens temporary wade lanes (design doc behavior) | Underground §8; Biome plan weather matrix. | Open
IO-W6-01 | W6 | Biome region B7 + precursor vault approach | World art + Narrative | IO-W5-01, GDD B4 #8 Aether-9 / Memory Cores | IO-W6-02, IO-W6-03 | B7 Ruin Belt surface; silent zones; vault lock POIs; android patrol routes. | - [ ] Silent escort activity playable - [ ] Corrupted Patrol Android patrol loops - [ ] Ecology checklist §5 B7 | Biome plan B7. | Open
IO-W6-02 | W6 | Stratum 4–5 instances + Still Hunter trace | World art + Content | IO-W6-01, IO-W5-01 | — | Geothermal S4 (Heat Eel); Resonance S5 vaults (Echo Lichen puzzles, symbiont swarm); Still Hunter myth ambient. | - [ ] S5 Saturation drift on loud combat in lichen zones - [ ] Still Hunter trace: flee encounter, codex entry, no farm - [ ] Aether seep scan POIs for Memory Core thread | Underground P5; Ecology B7/S5. | Open
IO-W6-03 | W6 | Pets batch final — C12 + V4 Echo Mote | Content | IO-W6-01, IO-W3-04 | — | Core-Sniffer Pup (B7 repair); Echo Mote vanity (B7 silent zone). | - [ ] All **12 core + 4 vanity** obtainable in campaign without DLC - [ ] C12 resonance loot ping functional | Phase map §4. | Open
IO-W7-01 | W7 | ExperienceDirector integration (Echo, elites, activities) | Systems | IO-W0-05, IO-W2–W6 content, GDD B4 #3 WorldState | IO-W8-05 | Live director: biome unlock mask, Echo weights, Void Stitcher pool, activity template weights, pet POI anchors (authored only). | - [ ] No static “always one Echo here” — weights per biome plan §2.8 - [ ] Stitcher max 1/expedition enforced - [ ] Strain/colony inputs reduce Echo/pet POI density when overwhelmed | Biome plan §2.8; Phase map W7. | Open
IO-W7-02 | W7 | Per-biome encounter tables + patrol polish | Content + Engineering | IO-W2-04, IO-W3-03, all biome regions | — | Final `SurfaceEncounterTable` per biome; patrol coverage; flying spawn budgets. | - [ ] Each biome B1–B7 has encounter table asset - [ ] Flying fauna caps per ecology §4.4 - [ ] Android + fauna never same anchor (spawn rules) | Ecology §4.5. | Open
IO-W7-03 | W7 | Activity grammar full set | Systems + Design | IO-W2-02, IO-W7-01 | — | Remaining templates: Echo Rescue, Salvage Run, Survey Sample, Depth Push, Core Recovery, Escort Extract. | - [ ] At least 8 templates defined; 2+ playable per biome category in test - [ ] Director can weight by colony need (O₂ low → condensate jobs) | Biome plan §6. | Open
IO-W7-04 | W7 | Weather × ecology coupling pass | Systems | IO-W5-02, WeatherDirector full | — | Ash gale embed spouts; storm fauna suppress; resonance supercell Stitcher spike. | - [ ] Sulfur storm suppresses surface combat spawns - [ ] Ash gale embeds dust spouts in B3 - [ ] Documented in debug overlay | Ecology §1.3; Phase map W7. | Open
IO-W7-05 | W7 | Ops radio + pet/Stitcher comms lines | Narrative + Communications | GDD B4 #2 Communications, IO-W3-02 | — | Template lines: biome warnings, pet tame hints, Void Stitcher first encounter, polar night warning. | - [ ] At least 5 template strings in comms system - [ ] Triggered by director/context builder stubs | Biome plan §2.6 comms. | Open
IO-W8-01 | W8 | Io Buggy (6-wheel) + deploy zones | Engineering + Content | IO-W1-01 vehicle tags, IO-W7-02 | — | Inventory-packed Io Buggy; path-tagged B3/B6; blocked B4/B5; pack at breach. | - [ ] Manual unpack in deploy zone; auto-pack 10–20 m at breach - [ ] Env resistance profile per biome table | Biome plan E8, vehicle table §2.5. | Open
IO-W8-02 | W8 | Hovercraft biome gates enforced | Engineering | IO-W8-01 | — | Enforce per-region hovercraft/buggy allow table on main map. | - [ ] B4/B5 reject vehicle deploy with player-facing message - [ ] Colony flats allow both types per table | Biome plan §2.5 vehicle table. | Open
IO-W8-03 | W8 | Console pet + expedition UX | UI + Input | IO-W2-05 | — | Gamepad pet summon/dismiss, skill activate, readable skill icons on TV safe area. | - [ ] Full pet loop on gamepad without keyboard - [ ] UI palette per `SurvivalPioneerUiPalette` | UI palette rule; GDD A9. | Open
IO-W8-04 | W8 | Performance pass (ambient fauna + instances) | Engineering | IO-W7-02 | — | Pool ambient skitters/moths; unload underground instances; encounter budget profiling on target hardware. | - [ ] Soft caps from phase map §5 encounter budget documented in profiler notes - [ ] No leak on breach cycle ×10 | Phase map encounter budget. | Open
IO-W8-05 | W8 | DLC pet pipeline hook | Engineering + Design | IO-W0-03, IO-W7-01 | Post-ship content | `PetDefinition.isDlc` + optional addressable load; vanity/core extension without schema break. | - [ ] New pet row can ship without code fork - [ ] Documented in ecology roster §7 DLC table - [ ] No paywall on core 12 in base game | Phase map §7; Ecology §4.6. | Open